## FrontEnd - Bug Report
|  |  |  | BUG OVERVIEW |  |  | ENVIRONMENT |  |  | BUG DETAILS |  |  | BUG TRACKING |  |  |  | FIX |  | NOTES
BUG ID | TITLE | REPORTED BY | DATE REPORTED | SUMMARY | URL | SCREENSHOT | PLATFORM | OPERATING SYSTEM | BROWSER | STEPS TO REPRODUCE | EXPECTED RESULT | ACTUAL RESULT | DEFECT SEVERITY | DEFECT PRIORITY | ASSIGNED TO | STATUS | RESOLUTION | DATE OF FIX | NOTES
BID001 | DGGOLD Unified Portal |  |  | After Successful Buy transaction, the success message is having spelling error - "Congratulations, your 38.462g Gold purchase has been succefully completed and booked to your secured vault account." |  |  | Windows | Windows 8.1 | Chrome |  |  |  | Low | Low |  | Open
BID002 | DGGOLD Unified Portal |  |  | Admin generated the Invoice from Admin panel, the invoice is not available in Customer Ordetr History Dashboard. It will be available only after Status changed to Success. But it shoul;d be available after the status changed to Invoice Generated |  |  | Windows | Windows 8.1 | Chrome |  |  |  | Major | High |  | Open
BID003 | DGGOLD Unified Portal |  |  | User shouldn't be able to add decimal value in price amount in Buy and Sell. But user can add decimal value as wish |  |  | Windows | Windows 8.1 | Chrome |  |  |  | Major | High |  | Open
BID004 | DGGOLD Unified Portal |  |  | User should be able to add upto 4 decimal places in the gram. But user is able to add upto 3 decimal places. |  |  | Windows | Windows 8.1 | Chrome |  |  |  | Major | High |  | Open
BID005 | DGGOLD Unified Portal-Sign up |  |  | Terms and condition mandatory field error message is overlapping |  |  | Windows | Windows 8.1 | Chrome |  |  |  | Minor | Low |  | Open
BID006 | DGGOLD Unified Portal-Sign up |  |  | After click on Terms and condition mandatory, link is not opening, it comes to home page |  |  | Windows | Windows 8.1 | Chrome |  |  |  | Minor | Low |  | Open
BID007 | DGGOLD Unified Portal |  |  | After entering OTP user got resgistered But Sign in page is buffering |  |  | Windows | Windows 8.1 | Chrome |  |  |  | Major | High |  | Open
BID008 | DGGOLD Unified Portal |  |  | If we enter OTP After 10 mins User got registered |  |  | Windows | Windows 8.1 | Chrome |  |  |  | Major | High |  | Open
BID009 | DGGOLD Unified Portal |  |  | After Buy Processing we came to Payment page, copy the url ana paste different browser, and enter payment details, user can buy successfully without any session |  |  | Windows | Windows 8.1 | Chrome |  |  |  | Major | High |  | Open
BID010 | DGGOLD Unified Portal |  |  | In Change mobile no Spelling mistake is there "Let's vetify its you. Please put answer exactly wjat used at sign up" |  |  | Windows | Windows 8.1 | Chrome |  |  |  | Low | Low |  | Open
BID011 | DGGOLD Unified Portal - Bank Details |  |  | In Banking Details - mandatory mark is missing for Bank Passbook/Chequebook Photo |  |  | Windows | Windows 8.1 | Chrome |  |  |  | Minor | Medium |  | Open
BID012 | DGGOLD Unified Portal - Portfolio Statement |  |  | Pagination is missing |  |  | Windows | Windows 8.1 | Chrome |  |  |  | Major | Medium |  | Open
BID013 | DGGOLD Unified Portal |  |  | My Rewards Menu is missing in Account |  |  | Windows | Windows 8.1 | Chrome |  |  |  | Minor | Medium |  | Open
BID014 | DGGOLD Unified Portal |  |  | Change the text in Change Mobile - Change Mobile No. to Change Mobile Number |  |  | Windows | Windows 8.1 | Chrome | Block the user then unblock the user from admin panel | user should be able to log in after unblock | User is not able to log in after unblock from admin panel
BID015 | DGGOLD Unified Portal |  |  | App download link isn't working |  |  | Windows | Windows 8.1 | Chrome
BID016 | DGGOLD Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome
BID017 | DGGOLD Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome
BID018 | DGGOLD Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome
BID019 | DGGOLD Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome
BID020 | DGGOLD Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome
BID021 | DGGOLD Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome
BID022 | DGGOLD Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome
BID023 | DGGOLD Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome
BID024 | DGGOLD Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome
BID025 | DGGOLD Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome
BID026 | DGGOLD Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome
BID027 | DGGOLD Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome
BID028 | DGGOLD Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome

## DigiGold_MobApp
|  |  |  | BUG OVERVIEW |  |  | ENVIRONMENT |  |  | BUG DETAILS |  |  | BUG TRACKING |  |  |  | FIX |  | NOTES
BUG ID | TITLE | REPORTED BY | DATE REPORTED | SUMMARY | URL | SCREENSHOT | PLATFORM | OPERATING SYSTEM | BROWSER | STEPS TO REPRODUCE | EXPECTED RESULT | ACTUAL RESULT | DEFECT SEVERITY | DEFECT PRIORITY | ASSIGNED TO | STATUS | RESOLUTION | DATE OF FIX | NOTES
BID001 | DGGOLD Unified Portal |  |  | Data privacy Notice is not working |  |  | Android | Windows 8.1 | Chrome |  |  |  | Low | Low |  | Closed
BID002 | DGGOLD Unified Portal |  |  | In MobileApp, user buys Gold and click on proceed ,it goes into the payment page. If click on "back" it shows "We are sorry but the transaction failed.Reason: Cancelled by user. You will be redirected to DG Gold in 3 seconds". Afterthat automatically it goes into "Thank you" page and shows "Congratulations,your 0.0795g goldr purchase has been successfully completed and book to your secured vault account." |  |  | Android | Windows 8.1 | Chrome |  |  |  | Major | High |  | Closed
BID003 | DGGOLD Unified Portal |  |  | In Order History Previous page and Next page tabs are wrong |  |  | Android | Windows 8.1 | Chrome |  |  |  | Minor | Medium |  | Closed
BID004 | DGGOLD Unified Portal |  |  | In change mobile no "Let's vetify its you. Please put answer exactly what used at sign up" missing |  |  | Android | Windows 8.1 | Chrome |  |  |  | Major | High |  | Closed
BID005 | DGGOLD Unified Portal-Sign In |  |  | In Password field, when eye icon is present, the password should be visible and when eye icon is crossed, then the password should be masked |  |  | Android | Windows 8.1 | Chrome |  |  |  | Minor | Low |  | Closed
BID006 | DGGOLD Unified Portal-Portfolio Statement |  |  | Change the text from PrediousPage to Previous and NextPage to Next |  |  | Android | Windows 8.1 | Chrome |  |  |  | Minor | Low |  | Closed
BID007 | DGGOLD Unified Portal-Portfolio Statement |  |  | Digigold logo is white, it should be uniform across the whole platform |  |  | Android | Windows 8.1 | Chrome |  |  |  | Major | High |  | Closed
BID008 | DGGOLD Unified Portal-Portfolio Statement |  |  | Pagination is missing |  |  | Android | Windows 8.1 | Chrome |  |  |  | Major | High |  | Reopen
BID009 | DGGOLD Unified Portal-Order History |  |  | Change the text from PrediousPage to Previous and NextPage to Next |  |  | Android | Windows 8.1 | Chrome |  |  |  | Major | High |  | Open
BID010 | DGGOLD Unified Portal-Order History |  |  | Digigold logo is white, it should be uniform across the whole platform |  |  | Android | Windows 8.1 | Chrome |  |  |  | Low | Low |  | Open
BID011 | DGGOLD Unified Portal-Order History |  |  | Pagination is missing |  |  | Android | Windows 8.1 | Chrome |  |  |  | Minor | Medium |  | Open
BID012 | DGGOLD Unified Portal - Change Password |  |  | In Change Password, there should be 3 fields - 1. Current Password 2. New Password 3. Confirm New Password New password shouldn't be same as Old password |  |  | Android | Windows 8.1 | Chrome |  |  |  | Major | Medium |  | Open
BID013 | DGGOLD Unified Portal - Order History |  |  | User is unable to download the Invoice |  |  | Android | Windows 8.1 | Chrome |  |  |  | Minor | Medium |  | Open
BID014 | DGGOLD Unified Portal |  |  | While redeem the total gold was0.4995gram 3235, Rupees After redeem success it is showing 1 gm gold has been redeemed |  |  | Android | Windows 8.1 | Chrome | Block the user then unblock the user from admin panel | user should be able to log in after unblock | User is not able to log in after unblock from admin panel | Major | High |  | Open
BID015 | DGGOLD Unified Portal |  |  | Total price should be showing till 2 decimal places |  |  | Android | Windows 8.1 | Chrome
BID016 | DGGOLD Unified Portal |  |  | In sell user enter OTP and click on PROCEED, It shows "Sorry! your payment could not be done, please try again later" but in the Order History it is Showing Success |  |  | Android | Windows 8.1 | Chrome
BID017 | DGGOLD Unified Portal | [5 empty] | Android | Windows 8.1 | Chrome
BID018 | DGGOLD Unified Portal | [5 empty] | Android | Windows 8.1 | Chrome
BID019 | DGGOLD Unified Portal | [5 empty] | Android | Windows 8.1 | Chrome
BID020 | DGGOLD Unified Portal | [5 empty] | Android | Windows 8.1 | Chrome
BID021 | DGGOLD Unified Portal | [5 empty] | Android | Windows 8.1 | Chrome
BID022 | DGGOLD Unified Portal | [5 empty] | Android | Windows 8.1 | Chrome
BID023 | DGGOLD Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome
BID024 | DGGOLD Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome
BID025 | DGGOLD Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome
BID026 | DGGOLD Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome
BID027 | DGGOLD Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome
BID028 | DGGOLD Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome

## DigiSilver_MobApp
|  |  |  | BUG OVERVIEW |  |  | ENVIRONMENT |  |  | BUG DETAILS |  |  | BUG TRACKING |  |  |  | FIX |  | NOTES
BUG ID | TITLE | REPORTED BY | DATE REPORTED | SUMMARY | URL | SCREENSHOT | PLATFORM | OPERATING SYSTEM | BROWSER | STEPS TO REPRODUCE | EXPECTED RESULT | ACTUAL RESULT | DEFECT SEVERITY | DEFECT PRIORITY | ASSIGNED TO | STATUS | RESOLUTION | DATE OF FIX | NOTES
BID001 | DGGOLD Unified Portal |  |  | In MobileApp, Login with OTP, user puts registered number and continue, 1. OTP is not coming into that mobile number 2. In resend OTP after 180sec, automatically it has started to count 180 sec. again and again without clicking on resend OTP 3. In forgot password, OTP is not coming into that mobile number to change the password. |  |  | Windows | Windows 8.1 | Chrome |  |  |  | Low | Low |  | Open
BID002 | DGGOLD Unified Portal |  |  | In MobileApp, user buys silver and click on proceed ,it goes into the payment page. If click on "back" it shows "We are sorry but the transaction failed.Reason:Cancelled by user. You will be redirected to DG Gold in 3 seconds". Afterthat automatically it goes into "Thank you" page and shows "Congratulations,your 38.961g silver purchase has been successfully completed and book to your secured vailt account." |  |  | Windows | Windows 8.1 | Chrome |  |  |  | Major | High |  | Open
BID003 | DGGOLD Unified Portal-Portfolio Statement |  |  | Change the text from PrediousPage to Previous and NextPage to Next |  |  | Windows | Windows 8.1 | Chrome |  |  |  | Major | High |  | Open
BID004 | DGGOLD Unified Portal-Portfolio Statement |  |  | Digisilver logo is white, it should be uniform across the whole platform |  |  | Windows | Windows 8.1 | Chrome |  |  |  | Major | High |  | Open
BID005 | DGGOLD Unified Portal-Portfolio Statement |  |  | Pagination is missing |  |  | Windows | Windows 8.1 | Chrome |  |  |  | Minor | Low |  | Open
BID006 | DGGOLD Unified Portal-Order History |  |  | Change the text from PrediousPage to Previous and NextPage to Next |  |  | Windows | Windows 8.1 | Chrome |  |  |  | Minor | Low |  | Open
BID007 | DGGOLD Unified Portal-Order History |  |  | Digisilver logo is white, it should be uniform across the whole platform |  |  | Windows | Windows 8.1 | Chrome |  |  |  | Major | High |  | Open
BID008 | DGGOLD Unified Portal-Order History |  |  | Pagination is missing |  |  | Windows | Windows 8.1 | Chrome |  |  |  | Major | High |  | Open
BID009 | DGGOLD Unified Portal - Change Password |  |  | In Change Password, there should be 3 fields - 1. Current Password 2. New Password 3. Confirm New Password New password shouldn't be same as Old password |  |  | Windows | Windows 8.1 | Chrome |  |  |  | Major | High |  | Open
BID010 | DGGOLD Unified Portal - Change Mobile |  |  | In change mobile no "Let's vetify its you. Please put answer exactly what used at sign up" missing |  |  | Windows | Windows 8.1 | Chrome |  |  |  | Low | Low |  | Open
BID011 | DGGOLD Unified Portal |  |  | Data privacy Notice is not working |  |  | Windows | Windows 8.1 | Chrome |  |  |  | Minor | Medium |  | Open
BID012 | DGGOLD Unified Portal - Order History |  |  | User is unable to download the Invoice |  |  | Windows | Windows 8.1 | Chrome |  |  |  | Major | Medium |  | Open
BID013 | DGGOLD Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome |  |  |  | Minor | Medium |  | Open
BID014 | DGGOLD Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome | Block the user then unblock the user from admin panel | user should be able to log in after unblock | User is not able to log in after unblock from admin panel
BID015 | DGGOLD Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome
BID016 | DGGOLD Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome
BID017 | DGGOLD Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome
BID018 | DGGOLD Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome
BID019 | DGGOLD Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome
BID020 | DGGOLD Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome
BID021 | DGGOLD Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome
BID022 | DGGOLD Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome
BID023 | DGGOLD Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome
BID024 | DGGOLD Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome
BID025 | DGGOLD Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome
BID026 | DGGOLD Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome
BID027 | DGGOLD Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome
BID028 | DGGOLD Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome

## Admin Panel - Bug Report
BUG ID |  |  |  | BUG OVERVIEW |  |  | ENVIRONMENT |  |  | BUG DETAILS |  |  | BUG TRACKING |  |  |  | FIX |  | NOTES
BUG ID | TITLE | REPORTED BY | DATE REPORTED | SUMMARY | URL | SCREENSHOT | PLATFORM | OPERATING SYSTEM | BROWSER | STEPS TO REPRODUCE | EXPECTED RESULT | ACTUAL RESULT | DEFECT SEVERITY | DEFECT PRIORITY | ASSIGNED TO | STATUS | RESOLUTION | DATE OF FIX | NOTES
BID001 | DG Unified Portal - Customer |  |  | User isn't able to Search any Customer. Need a search Customer Field |  |  | Windows | Windows 8.1 | Chrome |  |  |  | Minor | Medium |  | Reopen |  |  | SB: Changed Usernm to 'Senco', but still user can login with 'senco'
BID002 | DG Unified Portal - Order Management |  |  | The date format is showing like this - 2023-05-01T11:30:46.832000Z It should be 2023-05-01 11:30:46 and the Column name should be Date and Time |  |  | Windows | Windows 8.1 | Chrome |  |  |  | Minor | Medium |  | Closed
BID003 | DG Unified Portal - Store Management |  |  | Search doesn't work properly, i.e. - search with 'lak', it will render non-matching data also in the table |  |  | Windows | Windows 8.1 | Chrome |  |  |  | Minor | Medium |  | Closed
BID004 | DG Unified Portal |  |  | After user buy some gold, admin approved it ,transaction status is success. when admin validate buy dashboard( in all cards)- 1. In success , it is not updating the value. 2. In amount, it is not updating the value. 3. In weight, it is not updating the value. |  |  | Windows | Windows 8.1 | Chrome |  |  |  | Minor | Medium |  | Closed
BID005 | DG Unified Portal |  |  | After user sell some gold, admin approved it ,transaction status is success. when admin validate sell dashboard( in all cards)- 1. In weight, it is not updating the value. |  |  | Windows | Windows 8.1 | Chrome |  |  |  | Minor | Medium |  | Closed
BID006 | DG Unified Portal |  |  | After user redem some gold, transaction status is pending,when admin validate redem dashboard( in all cards)- 1. In amount, it is not updating the value. 2. In weight, it is not updating the value. |  |  | Windows | Windows 8.1 | Chrome |  |  |  | Minor | Medium |  | Reopen |  |  | SB: accepting 'senco@senco' as mail id
BID007 | DG Unified Portal |  |  | In "My digisilver" front end " Redem" option is not present but it is present in"My digisilver Dashboard" |  |  | Windows | Windows 8.1 | Chrome |  |  |  | Minor | Medium |  | Open
BID008 | DG Unified Portal |  |  | In"Admin Pannel" user after change the mobile number,click on" send OTP" ,message shows " OTP has sent successfully and it is valid upto 3 mins" but "OTP" is not coming into that mobile number. |  |  | Windows | Windows 8.1 | Chrome |  |  |  | Minor | Medium |  | Reopen
BID009 | DG Unified Portal |  |  | User attempts after10 times "sign in", blocked the user account and message is showing"You have exhausted your attempt to login & your account is temporarily blocked. Please contact Customer Care for further assistance."but in admin dashboard it is showing" Login status-Active" |  |  | Windows | Windows 8.1 | Chrome |  |  |  | Minor | Medium |  | Closed
BID010 | DG Unified Portal |  |  | If user changes profit percentage from Admin,after login, user buys some gold in "Buy in Rupees"/"Buy in g" click on proceed, message is showing"Metal rate mismatched , try again". |  |  | Windows | Windows 8.1 | Chrome |  |  |  | Minor | Medium |  | Closed
BID011 | DG Unified Portal |  |  | In "SMS logs report" user selects"Search by platform-All"," Search by mobile number-824096211"click on "Go", it comes to undefined Array key "platform" |  |  | Windows | Windows 8.1 | Chrome |  |  |  | Minor | Medium |  | Open
BID012 | DG Unified Portal |  |  | Admin generated the Invoice from Admin panel, the invoice is not available in Customer Ordetr History Dashboard. It will be available only after Status changed to Success. But it should be available after the status changed to Invoice Generated |  |  | Windows | Windows 8.1 | Chrome |  |  |  | Minor | Medium |  | Open
BID013 | DG Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome |  |  |  | Minor | Medium |  | Open
BID014 | DG Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome |  |  |  | Minor | Medium |  | Open
BID015 | DG Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome |  |  |  | Minor | Medium |  | Open
BID016 | DG Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome |  |  |  | Minor | Medium |  | Open
BID017 | DG Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome |  |  |  | Minor | Medium |  | Open
BID018 | DG Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome |  |  |  | Minor | Medium |  | Open
BID019 | DG Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome |  |  |  | Minor | Medium |  | Open
BID020 | DG Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome |  |  |  | Minor | Medium |  | Open
BID021 | DG Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome |  |  |  | Minor | Medium |  | Open
BID022 | DG Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome
BID023 | DG Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome
BID024 | DG Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome
BID025 | DG Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome
BID026 | DG Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome
BID027 | DG Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome
BID028 | DG Unified Portal | [5 empty] | Windows | Windows 8.1 | Chrome

## Summary
Module | Submodule | Status | Issues | Resolved | Pending | Remarks